## Sprint-1
Week #1 (28 hrs / week)
Backlog Item | Task | Task Owner | Initial Estimate (Total Sprint Hours = 7 x4) | D1 | D2 | D3 | D4 | D5 | D6 | D7
|  |  |  | 2021-10-07 | 2021-10-08 | 2021-10-09 | 2021-10-10 | 2021-10-11 | 2021-10-12 | 2021-10-13
28
Requirement discussion, Technology stack discussion | Researching about MERN | All | 4 | 4 | 3 | 2 | 1 | 1 | 1 | 0
| WireFrames design | All | 4 | 4 | 2 | 2 | 2 | 2 | 1 | 0
| Requirement Analysis | All | 6 | 6 | 5 | 5 | 4 | 2 | 1 | 0
| Learning ReactJS for Front end | Ishaan&Tarun | 5 | 5 | 4 | 4 | 3 | 3 | 2 | 0
| Learning Mongo DB atlas | All | 5 | 5 | 3 | 3 | 2 | 2 | 1 | 0
| Learning NodeJS | Rakesh&Mathu | 4 | 4 | 4 | 3 | 3 | 2 | 1 | 0
|  | Total | 28 | 28 | 24 | 23 | 17 | 13 | 8 | 0
Team: |  | Ideal time |  | 28 | 21 | 14 | 7 | 0
Ishaan Bhalla | 7 hours / Week
Raajmaathangani sreevijay | 7 hours / Week
Tarun kasturi | 7 hours / Week
Rakesh Nagarajappa | 7 hours / Week
Total Available Hours During Sprint: | 28

## Sprint-2
2021-10-14 |  |  |  | Week #2 (28 hrs / week)
Backlog Item | Task | Task Owner | Initial Estimate (Total Sprint Hours = 7 x 4) | D1 | D2 | D3 | D4 | D5 | D6 | D7
|  |  |  | 2021-10-14 | 2021-10-15 | 2021-10-16 | 2021-10-17 | 2021-10-18 | 2021-10-19 | 2021-10-20
28
Application Flow Understanding and setting up DB | Class Diagram | All | 5 | 5 | 5 | 4 | 2 | 0 | 0 | 0
| Mongo Schema | All | 5 | 5 | 5 | 4 | 4 | 3 | 1 | 0
| Flow of app | All | 7 | 7 | 7 | 6 | 6 | 4 | 2 | 0
| UI | All | 4 | 4 | 4 | 4 | 3 | 2 | 1 | 0
| Frontend setup | All | 3 | 3 | 2 | 1 | 0 | 0 | 0 | 0
| Backend setup | Rakesh & Mathu | 4 | 4 | 4 | 2 | 2 | 1 | 1 | 0
|  | Total | 28 | 28 | 23 | 20 | 16 | 10 | 5 | 0
Team:
ishaan bhalla | 7 hours / Week
Tarun Kasturi | 7 hours / Week
Rakesh | 7 hours / Week
Rajmathangani | 7 hours / Week
Total Available Hours During Sprint: | 28

## Sprint-3
Week #3 (7 hrs / week)
Backlog Item | Task | Task Owner | Initial Estimate (Total Sprint Hours = 7 x 4) | D1 | D2 | D3 | D4 | D5 | D6 | D7
|  |  |  | 2021-10-21 | 2021-10-22 | 2021-10-23 | 2021-10-24 | 2021-10-25 | 2021-10-26 | 2021-10-27
28
DB and API main task | Mongo Created for flight data | Ishaan&Rakesh | 4 | 4 | 4 | 3 | 2 | 1 | 1 | 0
| Mongo for user data | Ishaan&Rakesh | 3 | 3 | 2 | 2 | 1 | 1 | 0 | 0
| API building and function | Rakesh&Mathu | 5 | 5 | 4 | 3 | 2 | 1 | 0 | 0
| Login, Sign Up and Home pages | Ishaan&Tarun | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0
| Wireframes for Home, Login, SignUp | Rakesh | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 0
| Wireframes for Search Flights, Admin | Mathu | 4 | 4 | 4 | 3 | 2 | 1 | 0 | 0
| React Website integration | Ishaan | 6 | 6 | 5 | 4 | 2 | 1 | 0 | 0
| React background coding | Tarun | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0
|  |  | 28 | 28 | 25 | 21 | 15 | 10 | 2 | 0
Ideal Values
Team:
Ishaan bhalla | 7 hours / Week
Rakesh | 7 hours / Week
Raajmathangani | 7 hours / Week
Tarun | 7 hours / Week
Total Available Hours During Sprint: | 28

## Sprint-4
Week #4 (7 hrs / week)
Backlog Item | Task | Task Owner | Initial Estimate (Total Sprint Hours = 7 x 4) | D1 | D2 | D3 | D4 | D5 | D6 | D7
|  |  |  | 2021-10-28 | 2021-10-29 | 2021-10-30 | 2021-10-31 | 2021-11-01 | 2021-11-02 | 2021-11-03
28
UI and integration | Frontend for Home, LogIn, SignUp pages | Ishaan&Tarun | 5 | 5 | 4 | 3 | 2 | 2 | 0 | 0
| Wireframe for login | Rakesh | 2 | 2 | 2 | 2 | 1 | 1 | 0 | 0
| API to get flight data | Rakesh&Mathu | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 0
| API to add flight and delete | Rakesh&Mathu | 4.5 | 4.5 | 3 | 2 | 1 | 1 | 1 | 0
| Data add to db | Rakesh | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0
| learning canvas & particles in react | Ishaan&Mathu | 5 | 5 | 4 | 3 | 2 | 2 | 1 | 0
| Reward points integration | Mathu | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0
| API and DB integration | Rakesh&Mathu | 5 | 5 | 4 | 3 | 3 | 2 | 1 | 0
| DB management and checking | Rakesh | 2 | 2 | 2 | 1 | 0 | 0 | 0 | 0
|  |  | 28 | 28 | 22 | 16 | 11 | 9 | 4 | 0
Team:
Ishaan | 7 hours / Week
Tarun | 7 hours / Week
Rakesh | 7 hours / Week
Raajmathangani | 7 hours / Week
Total Available Hours During Sprint: | 28

## Sprint-5
Week #5 (7 hrs / week)
Backlog Item | Task | Task Owner | Initial Estimate (Total Sprint Hours = 7 x 4) | D1 | D2 | D3 | D4 | D5 | D6 | D7
|  |  |  | 2021-11-04 | 2021-11-05 | 2021-11-06 | 2021-11-07 | 2021-11-08 | 2021-11-09 | 2021-11-10
28
Final push | Booking page creation | Ishaan | 4 | 4 | 3 | 2 | 1 | 0 | 0 | 0
| Rewards setup | Mathu | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 0
| Mileage points db setup | Rakesh | 3 | 3 | 3 | 2 | 1 | 0 | 0 | 0
| Admin setup | Mathu | 4 | 4 | 4 | 4 | 3 | 2 | 1 | 0
| UI to search flights | Tarun | 2 | 2 | 2 | 1 | 0 | 0 | 0 | 0
| UI to show flights | Ishaan | 5 | 5 | 4 | 3 | 2 | 2 | 1 | 0
| API to fetch flight | Rakesh | 2 | 2 | 2 | 2 | 1 | 1 | 0 | 0
| AWS | Tarun | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
| Documentation | Ishaan | 4 | 4 | 3 | 2 | 2 | 2 | 1 | 0
|  |  | 28 | 28 | 24 | 19 | 12 | 8 | 4 | 0
Team:
Ishaan | 7 hours / Week
Tarun | 7 hours / Week
Raajmathangani | 7 hours / Week
Rakesh | 7 hours / Week
Total Available Hours During Sprint: | 28